## Idea Scorecard
Project idea | Type | Feasibility (1-5) | Skill fit (1-5) | Usefulness (1-5) | Time fit (1-5) | Cost fit (1-5) | Weighted score /100 | Notes
Student Project Progress Tracker and Report Assistant | Workflow / productivity | 5 | 5 | 5 | 4 | 5 |  | Initial estimate only; validate with guide and actual constraints
College Event Registration Portal | Web application | 4 | 4 | 4 | 4 | 4 |  | Initial estimate only; validate with guide and actual constraints
Library Book Availability Tracker | Database / web | 4 | 4 | 4 | 4 | 4 |  | Initial estimate only; validate with guide and actual constraints
Campus Lost-and-Found Board | Web application | 4 | 4 | 5 | 4 | 4 |  | Initial estimate only; validate with guide and actual constraints
Student Attendance Dashboard | Data dashboard | 4 | 4 | 4 | 4 | 3 |  | Initial estimate only; validate with guide and actual constraints
Personal Expense Tracker | Mobile/web | 4 | 4 | 4 | 4 | 4 |  | Initial estimate only; validate with guide and actual constraints
Study Timetable Planner | Web / productivity | 5 | 5 | 4 | 5 | 5 |  | Initial estimate only; validate with guide and actual constraints
Canteen Menu and Feedback Portal | Web application | 4 | 4 | 4 | 4 | 4 |  | Initial estimate only; validate with guide and actual constraints
Department FAQ Assistant (human-reviewed) | No-code AI | 4 | 4 | 4 | 4 | 3 |  | Initial estimate only; validate with guide and actual constraints
Lab Equipment Booking Tracker | Database / workflow | 4 | 4 | 4 | 3 | 4 |  | Initial estimate only; validate with guide and actual constraints

## Milestones
Week | Milestone | Tasks | Owner | Evidence / deliverable | Status
1 | Topic and scope | Confirm target audience, problem statement, objectives, constraints | [Name] | Approved one-page scope | Not started
2 | Research | Use two AI research tools; verify official sources and college guidelines | [Name] | Research log and citations | Not started
3 | Idea shortlist | Score 10 ideas and confirm selected idea with guide | [Name] | Completed idea scorecard | Not started
4 | Planning | Build schedule, roles, risk register and readiness checklist | [Name] | Project plan workbook | Not started
5 | Documentation draft | Draft abstract, introduction, literature survey and design from verified notes | [Name] | Report draft v1 | Not started
6 | No-code prototype | Build form → spreadsheet → draft status report with approval step | [Name] | Workflow and screenshots | Not started
7 | Testing and presentation | Run test cases, record failures, prepare 7 slides and viva quiz | [Name] | Test log, deck and quiz | Not started
8 | Final review | Correct issues, verify citations, complete before/after analysis and demo | [Name] | Final pack and demo evidence | Not started

## Risk Register
ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Fallback | Owner | Status
R1 | Free tool limits change | 3 | 3 |  | Check current limits before build | Use a spreadsheet template manually | [Name] | Open
R2 | AI invents or distorts details | 4 | 4 |  | Compare every sentence with notes and sources | Rewrite manually; reject unsupported claims | [Name] | Open
R3 | College format differs | 3 | 4 |  | Ask guide for official template early | Reformat report before submission | [Name] | Open
R4 | Workflow integration fails | 3 | 3 |  | Test each step with sample data | Use manual copy/paste workflow | [Name] | Open
R5 | Sensitive data shared accidentally | 2 | 5 |  | Use fictional data and review sharing permissions | Delete sample data and report incident per college policy | [Name] | Open
R6 | Insufficient testing time | 3 | 4 |  | Reserve Week 7 for testing | Prioritise core test cases and document gaps | [Name] | Open

## Readiness Checklist
Area | Checklist item | Status | Evidence / notes
Scope | Target audience and problem statement are specific | Not started
Scope | Guide approved the selected project and scope | Not started
Research | Two AI research tools used and logged | Not started
Research | Official sources opened and verified manually | Not started
Ideas | Ten ideas scored using consistent criteria | Not started
Planning | Milestones have owners and dates | Not started
Planning | Risks have mitigation and fallback actions | Not started
Report | Abstract matches actual completed work | Not started
Report | Literature survey cites real sources | Not started
Report | Design explains workflow and data flow | Not started
Testing | Test cases have expected and actual results | Not started
Testing | Errors and limitations are reported honestly | Not started
Ethics | AI assistance disclosed according to college policy | Not started
Ethics | No fabricated citations, results or survey data | Not started
Presentation | Seven-slide review deck completed | Not started
Viva | Ten questions practised and answers checked | Not started
Demo | Workflow demonstrated using fictional data | Not started
Final | Before/after analysis and evidence attached | Not started

## Test Log
Test ID | Scenario | Input | Expected result | Actual result (fill after test) | Pass/Fail | Evidence / screenshot link | Correction needed
T1 | Normal progress entry | Week 1; 3 tasks complete; next task listed | Draft includes completed work, next tasks and week | PENDING | PENDING
T2 | Blocker present | Blocked by missing dataset | Blocker is preserved and clearly flagged | PENDING | PENDING
T3 | Missing required field | No week number | Workflow flags missing week or asks user to correct | PENDING | PENDING
T4 | Long notes | Several paragraphs of notes | Summary keeps key facts without inventing details | PENDING | PENDING
T5 | Incorrect AI claim | Draft claims task is complete but notes say not started | Reviewer catches mismatch; draft is corrected/rejected | PENDING | PENDING
T6 | Privacy check | Fictional student/project data only | No personal or confidential information appears in output | PENDING | PENDING
T7 | Approval step | Draft generated but not yet reviewed | Report is not marked approved until human review | PENDING | PENDING

## Weekly Progress
Week | Completed work | Next tasks | Blockers | Evidence links | AI draft status summary | Human review notes | Approved by | Date
1 | [enter actual work] | [next tasks] | [blockers or None] | [links] | [draft only] | [review/corrections] | [name] | [date]